## Gantt Chart
Timeframe
| DETAILS | TASK OWNER | First 4 weeks | [23 empty] | Extra 12 weeks
|  |  | WEEK 9 | [5 empty] | WEEK 10 | [5 empty] | WEEK 11 | [5 empty] | WEEK 12 | [5 empty] | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
|  |  | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | Development Phase
1 | Project Conception
| Project Initiation | Group | bar: M; S
| Project Idea organization | Group | bar: M
| Meeting for discussion | Group | bar: M; M; M; M
| Virtual meeting (via online) | Group | bar: T to T; S; T; S to M; W; S; W to T; S
2 | Report
| Team Profile | Group | bar: T to W; M to T
| Tools | Group | bar: T; M to T
Project Description
| Topic | Taesung | bar: M to T
| Motivation | Taesung, Taehyeon | bar: T to W; F to S
| Landscape | Taehyeon | bar: T to S
Detailed Description
| Aims | Taesung, Taehyeon | bar: F to M; S to M
| Plans and Progress | Group | bar: T to W; W
| Roles | Group | bar: M to T; S to T; S to T; F
| Scope and Limits | Quan, Taesung | bar: T to F; M
| Tools and Technologies | Group | bar: W to F
| Testing | Jaejun | bar: F; T; F
| Timeframe | Taehyeon | bar: T to W
| Risks | Taehyeon | bar: T to S
| Group process and communications | Jaejun | bar: F; T; F
| Skills and Jobs | Group | bar: W
| Feedback | Group | bar: T to S
| Group Reflection | Group | bar: M; T to S
3 | Planning
| Define the technical architecture | Group | bar: F to S
| Pick a technology stack | Group | bar: F to S
4 | UI / UX Design
| Build Design System | Quan | bar: M to T; T; M; T; T; F to S
| Design app UI | Quan | bar: M to T; T; M to T; T to T; T to S
| Prototype UI | Quan | bar: F to S
| Design presentation | Quan | bar: T to S
| Design report website | Quan | bar: T to S
5 | App Development
| Back-End/Server | Taesung
| Database | Taesung
| Build a server (Social Network) | Taesung
| APIs (App Programming Interface) | Taesung
| Mobile App Front-End | Taesung
adding functions (Alarm,timetable,diet,etc.) | bar: M to T; T; M; F to S
Add contents | bar: M to T; T; M to T; T to T; F to S
6 | Testing
| Quality Assurance (QA) testing | Group | bar: M; F to S
| User Experience Testing | Quan | bar: M; F to S
| Functional Testing | Group
Performance Testing
| Security Testing | Group
| Device and Platform Testing | Group
7 | App Launch and Deployment
| Register developer account | Group
| Preparing metadata | Group
| Submmit the meta data | Group
| Waiting review process (for iOS) | Group
8 | Maintenence and Support
| Monitor through analytics platforms | Group
| Track Key Performance Indicators | Group
| Check crash reports / issues | Group
| Patch the app with improvement | Group
Milestone
Quan
Taesung
Jaejun
Taehyeon
All member participated